## CategorizingFeedback
asas | Feedback | Feedback Type | Desktop/iFrame Size | Orientation | Type | Priority | Browser | SS, might helpul | Status | Dev Team Comments | QC status R2 (11/7/21) | Dev Team Comments | QC status R3 (25/7/21) | Dev Team Comments | QC status R4 (26/7/21) | Dev Team Comments
a | Styling is not as per Zeplin e.g. text font style, Submit button alignment, bottom Category boxes size, card placement at dropping area. | Earlier Feedback by Latika | [6 empty] | Open | Fixed |  |  | Not fixed | fixed | Heading, Help instruction text, settings text style should be same as in matching template | verified with matching
a | Text is dithered please refer below screenshot: | Earlier Feedback by Latika | [6 empty] | Open | Fixed |  |  | Not fixed | fixed | Help and settings text is not updated as per new provided font as in matching template. | same as matching
a | Incorrect title added. | Earlier Feedback by Latika | [6 empty] | Verified and closed. | Fixed |  |  | Not fixed | fixed | Not fixed. Refer screenshot and matching template. | fixed
a | Hand cursor is not appearing on interactive elements. | Earlier Feedback by Latika | [6 empty] | Verified and closed. | Fixed |  |  | Not fixed | fixed | verified and closed
a | Snap back and replacing card functionality. | Earlier Feedback by Latika | [6 empty] | Open | Fixed |  |  | Not fixed | fixed | Not fixed: 1. User unable to snap back last card using keyboard. 2. User unable to snap the card using mouse also using following scenario: 1. User select the deck card then navigate to drop zone. 2. Now, select the card in drop zone. 3. Navigate to deck and try to snap back. 4. Nothing is happened and user unable to snap back. | fixed
a | Wave tool showing one error: | Earlier Feedback by Latika | [6 empty] | Open | Fixed |  |  | Not fixed |  | Please response | Please provide Title text. this is due to descriptive title text
a | Please make sure Zeplin design and production note, manuscript and accessibility guidelines should be implemented. If in case something in-progress, then please share the note with the build. | Earlier Feedback by Latika | [6 empty] | Open | Fixed |  |  | Not fixed | fixed | Issues are still open and mentioned in below sheet. | fixed
a
a | Correct the template title Composition Category Interactive instead Summary or Evaluation? | Global | All Iframe sizes |  | Naming Convention | Medium |  |  | Open | Fixed | Not Fixed | fixed | Not Fixed: Now, interactive heading is in correct please change to "Summary or Evaluation?" | fixed | Not Fixed: refer screenshot | fixed
a | Cards Functionality is not working properly. Refer to the video link: https://www.screencast.com/t/JKpKlsgIn | Global | All Iframe sizes |  | Functional | High |  |  | Open | Fixed | Not Fixed: Sometime user unable to place card in drop zone. |  | Not fixed | fixed | Due to extra card unable to place for correct answer. Please test in next build after removing of extra cards. | fixed
a | Replace the tool tip text showText with Instruction Text. | Global | All Iframe sizes |  | Accessibility | Medium |  |  | Open | Fixed | verified and closed
a | Replace the tool tip text setting with Color Contrast Settings. | Global | All Iframe sizes |  | Accessibility | Low |  |  | Open | Fixed | verified and closed
a | Top card changes it's positon. Please refer to the video link: https://www.screencast.com/t/DualrWQcVanE | Global | All Iframe sizes |  | UI + Functional | Medium |  |  | Open | Fixed | verified and closed
a | Category card should always be in the center. Currently, when user moves many cards in any of the category; position is incorrect. Please refer to the screenshot. | Global | All Iframe sizes |  | UI + Functional | Low |  |  | Open | Fixed (TBD) | Currently, limit added for item cards tin one category set to 6. |  | To limit cards in the category is not mentioned. Please don't limit it and please fix placement and alignment of all cards in ne category. | fixed | Verified and closed the alignment of 6 card in one category.
a | Global for buttons: Replace alt for "setting "with "Color Scheme Settings". Please use sentence case words for single words and capitalize each word for all words as stated Color Scheme Settings or Try Again. | Global | All Iframe sizes |  | Accessibility | Low |  |  | Open | Fixed | For setting icon screen reader read two alt text. Please replace with one "Color Scheme Settings". | fixed | Not Fixed: Screen reader should read "Color Scheme Settings" | fixed | Partially fixed: Using tab key screen reader reads both"Color Contrast Setting" "Color Scheme Settings" Please add only "Color Contrast Settings" as in Matching template. Also, change the tool tip as "Color Contrast Settings" | fixed
a | Dotted line appears in Desktop view. It is not as per zeplin design. TBD | Global | All Iframe sizes |  | UI | Low |  |  | Open | Fixed | verified and closed
a | Cards disappears when user clicks on the cards. Refer to the video link: https://www.screencast.com/t/l4P9C8AP4x0 Additionally, submit button appears. | Global | All Iframe sizes |  | Functionality | Medium |  |  | Open | Fixed | verified and closed
a | When cards disappeared and user clicks on submit button the card placement stack in the previous position. Refer to the screenshot. | Global | All Iframe sizes |  | UI + Functional | Medium |  |  | Open | Fixed | verified and closed
a | As per zeplin there should not be a gap in the categories in case of Incorrect/correct feedback. | Global | All Iframe sizes |  | UI | Medium |  |  | Open | Fixed | Not Fixed as per Zeplin. Red / green boarder is still having gape and it is clearly visible while zoom in. Please correct. | fixed and verified | verified and closed
a | Cards get cropped. Please correct the layout in 1350*760. Refer to the highlighted screenshot. | Global | 1350*760 |  | UI | Medium |  |  | Open | Fixed | verified and closed
a | Global for all settings button. Please increase the selection boundary and increase the width of the rectangle around the buttons. | Global | All |  | Accessibility | Low |  |  | Open | Fixed | verified and closed
a | All cards are not visible when user placed all the cards in one category. It should be 10 instead of 6. Refer to the screenshot. | Global | 1350*760 |  | UI | High |  |  | Open | Fixed | Currently, limit added for item cards tin one category set to 6. | This is as per zepline | It is not mentioned in Zeplin to limit the cards. Please check and fix. | fixed | Not Fixed | fixed
a | Please update heading one instead heading 2 for Main heading (Summary or Evolution?) | Global | All Iframe sizes |  | Accessibility | Medium |  |  | Open | Fixed | verified and closed
a | Close button placement is incorrect. Refer to the highlighted screenshots from zeplin and interactive. | Global | 1350*760 |  | UI | Low |  |  | Open | Fixed |  |  | Please fix this issue as per zeplin and client feedback. | fixed | Not Fixed, Should be consistent in all the templates i.e. in matching and in category. | fixed
a | Please increase the shadow effect for the cards as per Zeplin. | Global | All Iframe sizes |  | UI | Medium |  |  | Open | Fixed | verified and closed
a | Global for all buttons: Correct the buttons sizes as per zeplin. Example screenshot for Submit button. | Global | All Iframe sizes |  | UI | Medium |  |  | Open | Fixed | verified and closed
a | When user moved the last card position in another category; card snap back in the deck. For more clarity refer to the video URL. https://www.screencast.com/t/0seFeuA6M | Global | All Iframe sizes |  | Functional | Medium |  |  | Open | Fixed | snap back and change card category functionslity is not working. | Fixed | Snap back functionality is not working using keyboard. | fixed | Not fixed: 1. User unable to snap back last card using keyboard. 2. User unable to snap the card using mouse also using following scenario: 1. User select the deck card then navigate to drop zone. 2. Now, select the card in drop zone. 3. Navigate to deck and try to snap back. 4. Nothing is happened and user unable to snap back. | fixed
a | In one category if user moves more than six cards. The cards get disappeared. It should snap back to the initial stack. | Global | All Iframe sizes |  | Functional | Medium |  |  | Open | Fixed | Not Fixed: Now, user unable to move more than 6 cards. | as per zeplin design only 6 cards can be placed. | There is no production note in Zeplin to limit the cards, |  | Please fix. | fixed, can be placed all cards.
a | TBD this functionality with Vijay Sir as it should collapse the category but currently it is collapsing the cards. | Global | All Iframe sizes |  | Functional | Medium |  |  | Open | WIP |  | Fixed | Not fixed | fixed | verified and closed
a | Arrow icon is missing. Please refer to the screenshots. | Global | 650*365 |  | Functional | Medium |  |  | Open | Fixed | Partially fixed: First time is visible. When usr click on it then it disappeared. | Fixed | Not Fixed | fixed | Not fixed: Arrow missing.
a | Please correct the UI for help text. | Global | 650*365 |  | UI | Low |  |  | Open | Fixed | Help text design does not match with Zeplin. Text color is incorrect. | fixed | Not Fixed | fixed | Not fixed: Does not match with Zeplin and nor with Matching template. In both template it should be consistent. Also, Instruction text font is also different in both matching and category template. Please UI and text font. | fixed
a | Please update the scrolled in the left side too. It is working fine for the right arrow. Please bound the left limit too. | Global | 650*365 |  | Functional | Medium |  |  | Open | Fixed (TBD) |  |  | Please fix this issue as per zeplin and client feedback. | fixed | Not Fixed: both arrows are missing. And scroll bar UI does not match with Zeplin. | wip
a | Update the scrolled edges "round" instead "square" as per the zeplin design. Refer to the highlighted screenshot from zeplin and interactive. Also, update the width of the scrolled too. | Global | 650*365 |  | UI | Medium |  |  | Open | Fixed |  | Fixed (TBD) | Pleas fix |  | Not Fixed: Incorrect UI and and arrow sign are missing with Review button and with scrollbar. | wip
a | Dotted lines are missing for correct/incorrect feedback. Refer to the highlighted screenshot from zeplin and interactive. | Global | 650*365 |  | UI | Medium |  |  | Open | Fixed (checking) | Verified and closed
a | Button text seems dithered. Please ensure all the text size are as per zeplin. For an example refer to the screenshot. Global for all text font style. | Global | 650*365 |  | UI | Low |  |  | Open | Fixed, It's due to small font size | Card text (both top and bottom cards) font size is still small. | fixed | verified and closed
a | Update the feedback text as per the zeplin design. Refer to the highlighted screenshots from zeplin and interactive. | Global | 650*365 |  | UI | Medium |  |  | Open | WIP |  | fixed | verified and closed
a | Correct the help button text as per zeplin design. Refer to the highlighted screenshots from zeplin and interactive. | Global | 650*365 |  | UI | Low |  |  | Open | Fixed | Partially fixed: Text is updated but font size and color is not matched with Zeplin. | fixed | Not Fixed | fixed | Partially fixed: As Discussed please match instruction text and help pop-up UI with Matching template. | fixed
a | Increase the cue effect as per zeplin. | Global | 320*565 |  | UI | Low |  |  | Open | TBD |  |  | verified and closed
a | Please disable the Review Your Sorted Answers button until the user does not move the cards in the specific category. Refer to the video link: https://www.screencast.com/t/aJuNv2W4fFgx | Global | 320*565 (All applicable Iframe sizes) |  | Functional | Medium |  |  | Open | WIP |  | Fixed | Not fixed: Now, Review your Sorted Answer is remain appears disabled even user match the cards. | fixed | Not fixed the functionality of Review and Collapse category buttons is not working . Checked on real device. | fixed
a | Correct the UI as per zeplin for the help button text. Refer to the highlighted screenshot from zeplin and interactive. | Global | 320*565 |  | UI | Medium |  |  | Open | Fixed | Not fixed: incorrect Help text color and font size. | fixed | Not Fixed | fixed | Please fix as discussed should be consistent in all the template. | fixed
a | Submit button placement should be followed as per zeplin. Refer to the highlighted screenshot from zeplin and interactive. | Global | 320*565 |  | UI | Medium |  |  | Open | Fixed |  | Fixed | verified and closed
a | There is variability in zeplin design. For an example Reset and Try Again Buttons. Refer to the screenshots. | Global | All Iframe sizes |  | UI | Low |  |  | Open | Fixed |  | Fixed | verified and closed
a | Update the highlighted area for the incorrect and correct feedback text as per zeplin. Refer to the highlighted screenshot from zeplin and interactive. | Global | 320*565 |  | UI | Medium |  |  | Open | Fixed |  | Fixed | verified and closed
a | Update the cards stack as per zeplin. Small portion of the text is visible. Refer to the highlighted screenshots from zeplin and interactive. | Global | 530*943 |  | UI | Low |  |  | Open | Small text not visible as mentioned in comment |  | TBD | Please fix | fixed | Partially fixed: Visible in iframe view | fixed
a | Update the main heading position as per zeplin design. Refer to the highlighted screenshots from zeplin and interactive. | Global | 530*943 |  | UI | Medium |  |  | Open | Fixed |  |  | Not Fixed | fixed | Not fixed: As discussed should be consistent in both matching and category template heading font, color and position. Please fix | fixed
a | Text is not clear. Please ensure the font style as per zeplin design. | Global | 530*943 |  | UI | Medium |  |  | Open | Style is as per zapline. Text dithers due to samll size |  |  | Not Fixed | fixed | closing this issue
a | Submit Button placement is not as per zeplin design. Refer to the highlighted screenshots from zeplin and interactive. | Global | 530*943 |  | UI | Medium |  |  | Open | Fixed |  |  | verified and closed
a | Try Again buttons placement is not as per zeplin design. Also, one line is there above the incorrect and correct feedback text. Refer to the highlighted screenshots from zeplin and interactive. | Global | 530*943 |  | UI | Medium |  |  | Open | Fixed |  |  | Not Fixed, Incorrect position of feedback text and Try again button. | fixed | Not Fixed, Incorrect position of feedback text and Try again button. Also, line above feedback text is missing. In mobile and tablet : Submit, Try again and Reset button should appear at same position. Should not jump as in Desktop. | fixed
a | Mobile device: the highlighted area should be throughout the page. Refer to the highlighted screenshots from zeplin and interactive. | Global | 530*943 |  | UI | Medium |  |  | Open | Fixed |  |  | verified and closed
a | Please remove the button from the aria-label. SR defaults read the button. Global for all the buttons. Refer to the example screenshot: | Global | All |  | Accessibility | Medium |  |  | Open | Fixed |  |  | Partially Fixed: Please fix for Submit, Try again and Reset buttons. Screen reader reads aria-label twice. | fixed | Partially fixed: button name speak twice due to tool tip. As discussed please remove tool tip from Submit, Try again and Reset button. | fixed. tool tip removed from try again and Reset button.
a | Screen reader is reading the text "less" Please correct the alt of all the cards. Refer to the example screenshot. Refer to the video URL: https://www.screencast.com/t/TUgzLpCk4DIn | Global | All |  | Accessibility | Medium |  |  | Open | Fixed |  |  | verified and closed
a | Screen reader is reading the extra code after the categories. Refer to the screenshot. | Global | All |  | Accessibility | Medium |  |  | Open | checking |  |  | Please fix | fixed | verified and closed
a | Please check the close functionality for settings and help button. Refer to the video URL: https://www.screencast.com/t/bK8JH6lxPiq9 | Global | All |  | Keyboard (Accessibility) | Low |  |  | Open | change functionality | Fixed |  | closing this issue.
a | With screen readers and keyboard last card get selected first. Please check and implement . Refer to the video URL: https://www.screencast.com/t/yOwPg9gW | Global | All |  | Accessibility | Medium |  |  | Open | WIP |  |  | Please fix | same as matching | verified and closed
a | The instruction not followed: If a user selects a card in error while trying to scroll, selecting a second time, can undo the selection. | Global | All |  | Functionality | Medium |  |  | Open | Fixed | TBD |  | Please fix | fixed | Currently, In both Matching and Category last card is selected. Please check | as per matching template
a | Please advise if an additional visual cue is possible when the item drops in. Perhaps have the category background color flash to the gray #5E6062 and back to black when the Item drops in. | TBD | [7 empty] | TBD |  |  | Please fix |  | Please check and response | not possible
a
a | 7072022
a | There should be no gap in between the correct and incoorect outline as per zeplin. | Global | 1350*760 | Landscape mode (Desktop) | UI | Medium | Safari (Mac) |  |  | WIP | Fixed |  | Not fixed | fixed | Extra space is appearing at the top of first category. | fixed
a | Cards size should be consistent. Whatever the card size is for the large text it should be adopted by other cards. | Global | 1350*760 | Landscape mode (Desktop) | UI | Medium | Safari (Mac) |  |  | WIP | Fixed |  | Not fixed | fixed | verified and closed
a | All cards for category 2 is not visible on the screen. | Global | 1350*760 | Landscape mode (Desktop) | UI + Functional | Medium | Safari (Mac) |  |  | WIP | Fixed |  | User can add only 6 cards in one category. This is not mentioned in the Zeplin. | fixed | User unable to drop more than 6 cards. Please fix | fixed
a | Cards stack is not as per the zeplin due to different sizes of the text. Please make the cards size consistent. | Global | 1350*760 | Landscape mode (Desktop) | UI | Medium | Safari (Mac) |  |  | WIP | Fixed |  | Not fixed | fixed | closing
a | Crads size should be consistent. | Global | 650*365 | Landscape mode (Desktop) | UI | Medium | Safari (Mac) |  |  | WIP | Fixed |  | Alignment in drop area is not correct may be due to size difference. | fixed | closing
a | Other categories are not visible. | Global | 650*365 | Landscape mode (Desktop) | UI | Medium | Safari (Mac) |  |  | WIP | Fixed |  |  |  | as per manuscript, closing
a | Scroller is not visible for this size. | Global | 650*365 | Landscape mode (Desktop) | UI | Medium | Safari (Mac) |  |  | WIP | Fixed |  | Not fixed | fixed | Not Fixed | wip
a | When help instruction button is open settings buttons get cropped. Setting button changes it's position. | Global | 650*365 | Landscape mode (Desktop) | UI + Functional | Medium | Safari (Mac) |  |  | WIP | Fixed |  | Not fixed | fixed | Please fix position as per matching template. | fixed
a | Cards size is not consistent. Whenever there is a large text all the cards size should be as per that card with the largmaximum text. | Global | 530*943 | Portrait (Tablet) | UI | Medium | Safari (Mac) |  |  | WIP | Fixed |  | Not fixed | fixed | closing
a | Font style is different. | Global | 530*943 | Portrait (Tablet) | UI | Medium | Safari (Mac) |  |  | WIP | Fixed |  | Not fixed | fixed | For Heading, Help text and setting text - font should be same as in Matching. | fixed
a | Text is dithered in all devices. | Global | 530*943 | Portrait (Tablet) | UI | Medium | Safari (Mac) |  |  | WIP | Fixed |  | Check for instruction text and color scheme pop-up it is different as compare to matching template. | font and size is used as per zeplin | For Heading, Help text and setting text - font should be same as in Matching. | fixed
a | Try again button placement is different compared to zeplin. It should be near the dotted line. | Global | 530*943 | Portrait (Tablet) | UI + Functional | Medium | Safari (Mac) |  |  | WIP | Fixed |  | Not fixed | fixed | Closing.
a | when help buttton text is open and user clicks on settings button. The last clicked should be on top of the layer. So color scheme settings button should be visible. Please check with keyboard or touch devices. | Global | All | All devices | UI + Functional | Medium | All browsers |  |  | Fixed |  |  | verified and closed
a | Cross button icon seems different than the zeplin design. | Global | Iphone+Tablet | All devices other than desktop | UI | Medium | Safari (Mac) |  |  | Fixed |  |  | Not fixed | fixed | Please fix as in matching. | fixed
a | Hightlighted area for correct and incorrect is not as per zeplin. | Global | 320*565 | Portrait (Cell phone) Almost all devices | UI | Medium | Safari (Mac) |  |  | WIP | Fixed |  | Not fixed | fixed | Extra space at the top of 1st category so highlighter does not cover complete space. | fixed
a | With keyboard when user interact with keyboard focus also moves to the cards while placing the cards in the category. Is it feasible that focus should only move to the category fields only. | Global | All devices | All | Functional | Medium |  |  |  | WIP | Fixed |  | verified and closed
a | With keyboard when focus moves to the cards. The cards shifts. | Global | All devices | All | Accessibility | Medium |  |  |  | WIP | Fixed |  | Not Fixed | fixed | verified and closed
a | With keyboard as soon as the last card drops it's place it is feasible to get focus on Submit button. | Global | All devices | All | Accessibility | Medium |  |  |  | Fixed |  |  | Not Fixed |  | Please response | Since user has option to change answer, focus is not moved to submit
a | Last card snap back to it's previous stack position. I believe this point will be resolved with the previous point. However, sharing you the screenshot for reference. | Global | All devices | All | Functional | Medium |  |  |  | Fixed | Fixed |  | Not Fixed |  | Not fixed: Please fix as discussed with Vijay sir. | fixed
a | Screen reader reads the correct feedback in chunks. | Global | All devices | All | Accessibility | Very Low |  |  |  | TBD |  |  | Please check and fix |  | Please response | Screen reader issue
a | Correct the UI for all the tickmarks and cross icons. | Global | All | All | UI | Medium | Edge |  |  | WIP | Fixed |  | Not Fixed: Cross icons are not appeared in Edge. | fixed | verified and closed
a | For color scheme buttons screen reader does not read the selected color scheme. Please use aria-pressed="true" for selected one and aria-pressed="false" for non selected. | Global | All | All | Accessibility | Medium | All |  |  | WIP | Fixed |  | verified and closed
a | Screen reader announces the extra elemetnts in the cards. Please check and correct it. | Global | All | All | Accessibility | Medium | All |  |  | Fixed |  |  | verified and closed
a | Please share the limit for the XML verification. | Global | All | All | XML | Medium | All | [5 empty] | please give response |  | please give response | Successfuly tested with 30 cards
a | Please use different aria-label for settings close button and color scheme close button. For Color Scheme Button use Color Scheme Settings Close and for help button use Help instruction Close. Please ensure the screen reader reads the button once instaed twice. | Global | All | All | All | Low | All |  |  | WIP | Fixed |  | Not fixed | fixed | Not fixed: Please fix same as fixed in matching and given in the feedback | fixed
a | Please increase the stroke width for the focus selection as it is less visible to the user. Also, share the color code you have used for the border selection. Refer to the screenshot. Additionally, please check this link for color contrast selection that will pass in web accessibility. https://webaim.org/resources/contrastchecker/ | Global | All | All | Accessibility | Low | All |  |  | TBD |  |  | Please check and response | fixed | verified and closed
a | Scroller UI is not as per zeplin design. Please ensure to add the arrow too. | Global | 650*365 | All | UI | Medium | Firefox Browser (Windows) |  |  | WIP | TBD |  | please fix | fixed | Not Fixed: Arrows are not visible. | wip
a | Dotted line is missng in this layout for incorrect and correct area. |  | 650*365 | All | UI | Medium | Firefox Browser (Windows) |  |  | Fixed |  |  | Extra doted line appears at the bottom after category 2. Which is not present in Zeppelin. | fixed | Now, line is present but red and green border does not cover complete space in Firefox at top and bottom of the card. | fixed
a | Cards get cropped. Line seems normal. It should be dotted one.. | Global | 650*365 | All | UI |  | Firefox Browser (Windows) |  |  | Fixed |  |  | verified and closed | fixed
a | Cards size should be consistent. | Global | 650*365 | All | UI | Medium | Firefox Browser (Windows) |  |  | Fixed |  |  | verified and closed | fixed
a | Settings button position displaced. Steps to reproduce: 1: Click on color scheme settings button. 2. Click on help buton. 3. Setting button overlaps. It should not be there. Please check and fix. | All | All | All | All | Medium | All |  |  | Fixed |  | Fixed | verified and closed | fixed
[13 empty] | No hand icon on help, settings and close button. | fixed | verified and closed
[13 empty] | Cards text alignment change on card selection. Please correct. | fixed | Not Fixed | fixed
[13 empty] | Incorrect position of Help icon '?' in the black frame. | fixed | Does not match with matching template. | fixed
[13 empty] | On selecting any card, card are moving | fixed | Not Fixed | fixed
[13 empty] | double enter key, card should move to deck. |  | Please consistent functionality in both Matching and category template. | fixed
[13 empty] | Heading does not pass accessibility color contrast ratio guidelines on selecting color contrast second option i.e. green and ed. |  | open issue | used as provided
[13 empty] | For High contrast: User unable to distinguish between item cards. |  | open issue | used as provided
[13 empty] | Sometime user unable to select and drop card in second category using keyboard. When first category is filled. | fixed | closing this issue | fixed
[13 empty] | Extra dotted line appears at the bottom which is not given in Zeplin. | fixed | Not Fixed | wip
[13 empty] | Global : Please check the font : Heading, Instruction text, Color scheme font does not same as in Matching. Please both template font should be match for all elements. | fixed | Not fixed: Both template should be e consistent in heading , Help pop-up and text, settings pop-up and text. | fixed
[13 empty] | As discussed Remove tool tip from button in the Category template | fixed | Not Fixed | fixed
[13 empty] | Help and settings icon should be of same size and at same place in both Matching and Category template. Please fix. | fixed | Not Fixed | fixed
[13 empty] | Help pop-up size and close icon size should be same in both matching and category template. Also, close icon position should be same. | fixed | Not fixed | fixed
[13 empty] | setting pop-up size and close icon size should be same in both matching and category template. Also, close icon position should be same. | fixed | Not Fixed | fixed
[13 empty] | Client Feedback: he closing X in the instructions call out seems to be an odd chunky shape. compared to how it was in zeplin. Was there a request for this, or is it an error? - The items stack vertically even if the window is small. the hope for the iframe view was for the items to stack horizontally to be scrollable to the right side of the screen. Is this one of the UI items that is still being worked on? - I'll refer to Shelly on any text content. - The Helvetica fonts appear to be displaying well. -Please let us know when the UI will be fully operational." | fixed | Not fixed | fixed
[15 empty] | Duplicate cards has been added. Content should be as par manuscript then why it is s added. | fixed

## FontStyleCategory
| Layout | Desktop/iFrame Size | Heading | Top Card Text (Deck) | Category | Help (Instruction text) | Submit Button | 3 Category (Submit (Text) | Feedback Text | Reset Button (There is difference for Try Again and Reset buttons in Zeplin) | Reset (Text) | Incorrect Answers | Right Answers |  | SRM Comments | Status | Comments
Desktop iFrame size | Landscape | 650*365
Typeface |  |  | HelveticaNeue-Bold | HelveticaNeue-Regular | HelveticaNeue-Bold | HelveticaNeue-Regular | None | HelveticaNeue-Bold | HelveticaNeue-Regular | None | HelveticaNeue-Bold
Size |  |  | 14px | 12px | 14px | 12px | None | 13px | 14px | None | 13px
Align |  |  | Left | Left | Center | Left | None | Center | Left | None | Center
Line Height |  |  | 20px (line-height: 1.25;) | Normal | 16px | 18px | None | 16px | 20px | None | 16px |  |  |  | TBD. Please use 1.5 line height. Global for all templates.
Font Color |  |  | #000000 | #4a4a4a | #ffffff | #ffffff | N/A | #ffffff | #5e6062 | #d4450c | #ffffff
Background Color |  |  | #ffffff | #ffffff | #000000 | #6c6e70 | #d4450c | N/A | #ffffff
Color code for right answers |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | #63a524 | N/A
Opacity for right answers |  |  | 38% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 38% | N/A
Color code for incorrect answers |  |  | #63a524 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | #c22032 | N/A | N/A
Color code for incorrect answers |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 38% | N/A | N/A
Review your Sorted answer (Background color |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | #5e6062
Review your Sorted answer (Foreground color |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | #ffffff
Large desktop size | Landscape | 1350*760
Typeface |  |  | HelveticaNeue-Bold | HelveticaNeue-Regular | HelveticaNeue-Bold | HelveticaNeue-Regular | None | HelveticaNeue-Bold | HelveticaNeue-Regular | None | HelveticaNeue-Bold
Size |  |  | 20px | 16px | 18px | 18px | None | 20px | 18px | None | 20px
Align |  |  | Left | Left | Center | Left | None | Center | Left | None | Center
Line Height |  |  | 28px | #ffffff | 24px | 26px | None | Normal | 26px | None | Normal
Font Color |  |  | #000000 | #4a4a4a | #ffffff | #ffffff | N/A | #ffffff | #5e6062 | #d4450c | #ffffff
Background Color |  |  | #fafafa | N/A | #000000 | #5e6062 | #d4450c | N/A | #ffffff | N/A | N/A
Tablet size | Portrait | 530*943
Typeface |  |  | HelveticaNeue-Bold | HelveticaNeue-Regular | HelveticaNeue-Bold | HelveticaNeue-Regular | None | HelveticaNeue-Bold | HelveticaNeue-Regular | None | HelveticaNeue-Bold
Size |  |  | 16px | 14px | 16px | 14px | None | 15px | 16px | None | 16px
Align |  |  | Left | Left | Center | Left | None | Left (it should be center) | Left | None | Center
Line Height |  |  | 20px | 20px | 20px | 18px | None | 16px | 20px | None | 16px
Font Color |  |  | #000000 | #4a4a4a | #ffffff | #ffffff | N/A | #ffffff | #5e6062 | #d4450c | #fafafa
Background Color |  |  | #fafafa | #ffffff | #000000 | #5e6062 | #d4450c | N/A | #fafafa
Extra Small Phone size | Portrait (2 Category) | 320*565
Typeface |  |  | HelveticaNeue-Bold | HelveticaNeue-Regular | HelveticaNeue-Regular | HelveticaNeue-Regular | None | HelveticaNeue-Bold | HelveticaNeue-Regular | None | HelveticaNeue-Bold
Size |  |  | 16px | 14px | 16px | 14px | None | 16px | 16px | None | 16px
Align |  |  | Left | Left | Center | Left | None | Left | Left | None | Center
Line Height |  |  | 20px | Normal | 20px | 18px | None | 16px | 20px | None | 16px
Color |  |  | #000000 | #4a4a4a | #ffffff | #ffffff | N/A | #ffffff | #5e6062 | N/A | #ffffff
Background Color |  |  | #ffffff | #ffffff | #000000 | #5e6062 | #d4450c | N/A | #ffffff | #d4450c | N/A
* Please note all text for butons needs to be centered. Please ignore the above data entry for button text.

## LinkHistory
R2 build webshare link | https://webshares.sixredmarbles.com/vijay/2022/ops/ops-000727/categorizing/v2/categorizing/