## Sheet1
Issues | Dev comment | QC Comment R2 (08-08-22) | Dev comment
Begin Activity and Review Activity: Please correct the text and up arrow styling and alignment as per Zeplin. | Fixed | Not Fixed: Review activity is still truncated. Also, in iFrame and LMS Review Activity button is not visible at all. | unable to reproduce
Begin Activity and Review Activity: Please correct white oval space frame as per Zeplin. It does not match style. | Fixed | Not Fixed: does not match with Zeplin design.
Review Activity is not completely visible and hide from the top. Please correct as per Zeplin. | please mention screen size | My system reading: Width: 1366 height: 657 | Fixed
Instruction text: Incorrect instruction text. Please update as given in the Zeplin. | Fixed | verified and closed
Setting: Please correct the setting pop-up and cross icon size and position as per Category interactive. | Fixed | pop-up size, color scheme style, option position does not match with Category. | This is same as matching template
Incorrect color used for showing greyed out right and bottom part of second screen as per Zeplin. Please fix. | fixed | Not Fixed | copyed from zeplin. #707070 opacity 80%
White border size above Review Activity button does not match with Zepline. It is appearing very wide in Mac system and Windows it is very thin. | fixed | Not Fixed
Please correct the placement of interactive title , top cards, Bottom cards as per matching template. Please move little right side. | Fixed | Not Fixed
Please add dotted separation line after top cards and between bottom cards as per Zeplin. | Fixed | Not Fixed: Now, dotted line is missing before last row of the cards. | Not possible
Global: Incorrect content. Please add content i.e. title, card and feedback as per Zeplin. | Please provide content | Please update title and feedback text as per Zeplin for now. https://app.zeplin.io/project/61893d5e360ebe11e26ddd89/screen/62b66da83f692221143f228c
Reset button cannot verify in this build as incorrect content has been added.
Extra grey line appears in 3rd option card image. | Fixed | verified and closed
Incorrect UI for bottom cards when user scroll the page using verticle scroll bar. Bottom cards are appearing above the dotted line. | Fixed | verified and closed
Please correct position of main image as per Zeplin. Add more space at the top as in Zeplin. |  | verified and closed
When user Submit activity then cross and tick mark touches dotted line. Please add proper space as in Zeplin. | Fixed | verified and closed
iFrame view: In Zeplin for Ifram view first given arrow icon then Begin Activity and Review Activity button. | Not fixed |  | Not possible
iFrame view: Please add little space in instruction text and x icon so that they don't touch each other. | fixed | verified and closed
iFrame view: When user placed the top card in the drop zone then top card and dotted line are overlapping | Fixed | verified and closed
iFrame: Help pop-up : text and cross icon touches each other. Please correct | Fixed | verified and closed
iFrame: On scrolling top cards, bottom cards and submit and try again button are overlapping. | Fixed | verified and closed
iFrame: Please add correct margin at both left and right side as per Zeplin. | Fixed | verified and closed
iFrame view: Tick and cross icon truncated from right side | Fixed | Now, all cards are touching each other in a row. | please mention screen size
iFrame view: Horizontal scroll bar with arrow are missing. Please correct as in Zeplin. | WIP |  | Fixed
MAC: All Browser: Review activity button and Top cards are overlapping. Please add space as in Zeplin. | fixed | Not Fixed
Mobile Phone Portrait mode: Main image is truncated from the top. | Fixed | verified and closed
Mobile Phone Portrait mode: Review activity button and top cards are overlapping. | Fixed | Not fixed | working fine for me
Mobile Portrait mode: Feedback hide by Review Activity button. Please move feedback text little down as in Zeplin. | not reproduced | Not Fixed: Feedback text, submit button are still hide by top Review Activity and white border. And so content is truncated.
Mobile Portrait Mode: On scrolling, cards are truncated from the top. | Fixed | verified and closed
Mobile Land space Mode: On Scrolling, Top , bottom cards, Submit button are overlapped. | Fixed | Please correct the ratio of top portion and bottom portion. Now, top part taking unnecessary more space than bottom part.
Mobile Landscape mode: Help pop-up: Cross icon and text are overlapping. | Fixed | verified and closed
Mobile View: When user change from portrait to landscape mode then user found difficulty in scrolling screen. Please check. | Fixed | verified and closed
Tablet Portrait view: Main image is not set correctly. From top image is truncated and from bottom image is appearing out of frame. | Fixed | Now, Begin Activity button is truncated and appears in two line. | working fine
Tablet Portrait view: On clicking Begin Activity button then main image is still appearing at the top with Review activity button. Please correct UI. | Fixed | Not fixed | please mention screen size
Tablet View: Incorrect Review Activity button UI. Arrow icon in Review Activity button is appearing in next line and out of frame. Please correct UI. Refer above screenshot | fixed | Not fixed, refer above screenshot
Tablet View: Feedback text is truncated and hide from the top. Refer above screenshot | Fixed | Not Fixed: Feedback Text and try again button are misaligned.
Tablet Portrait View: Try Again button is truncated from the right side. | Fixed | Not Fixed: Button is misaligned. Refer above screenshot
Tablet View: Last card is appearing truncated and user unable to view by scrolling. | Fixed | Not Fixed
Tablet Landscape View: When user try to scroll the bottom Description cards then incorrectly top cards are scrolled but bottom cards are not scrolled. | Fixed | verified and closed
Tablet view: Top card text is not centre aligned. | Fixed | verified and closed
Tablet and Phone landscape mode: Begin Activity button should be visible without scroll. | Fixed | Not fixed for both Mobile phone and tablet devices.
Tablet landscape mode: Please correct alignment of Try again button. Align with Bottom cards properly. | Fixed | Not Fixed
Tablet View: Settings cross icon is truncated from the bottom. | Fixed | Not fixed
Tablet Landscape view: Bottom card images numbers are truncated. | Fixed | Not Fixed
Accessibility: Wave tool showing 10 errors. Please check and correct. | Fixed | verified and closed
Accessibility: Light house report showing error. Please correct. | Fixed | Not fixed:
Accessibility: Setting pop-up. Screen reader read Close twice for x icon. | Fixed | Not Fixed: Close button of both Settings and Help .
Accessibility: Incorrect areia label for Begin Activity. | Fixed | verified and closed
Accessibility: Focus is stuck on last Description to match card and screen reader reads card areia label again and again. Please navigate to browser tabs as in Matching template. | unable to reproduce | Using NVDA it is reproducible. Screen reader read mode full instead of navigating to browser top .
Accessibility: Incorrectly focus of greyed out screen on main screen image. Please fix | TBD
Accessibility: When user press enter on Begin Activity button then focus shifted to out of interactive screen instead of on Review activity button. | Fixed | now, selection blue boarder is remain at same visible at same place but buttons are working using keyboard.
Accessibility: For Bottom card add alt text as image 1,imag 2… so on for now. | Fixed | closed
Accessibility: Mac Safari: Focus is not appearing on Submit button using Tab key. | Fixed | Now, focus is not appearing on Submit button using arrow key.
Accessibility: Once user submit button then user unable to go to cards using tab keys after reset/ Try Again button tab move focus to browser top.
Try Again button is start appearing in two line. Please correct.
Please correct the spacing as per zeplin above the 1st row, above 2nd row, bottom of the 2nd row of the cards. Currently, there is no space after 2nd row. Please correct.